## Slide 1: Baseline in Safran Project
Processes and functionality

## Slide 2: Baseline in Safran Project
What happens under the hood of Safran Project when we set a baseline?
A reference plan is created based on scopes, dates and milestones
Information is stored in the baseline tables baseline_a (activity information) and baseline_r (resource information)
  Dates, durations, resource assignments, calendar information, and some progress data
  Change orders are committed to scope
Scopes are updated according to the scope settings in Project Properties
«Original» fields are updated if this is your first baseline run in the project. (If you don’t move timenow when re-baselineing the original fields will be overwritten
The baseline log is updated every time you run a baseline with baseline date, revision, comments and username of the person setting the baseline
This means that we build a library of baselines to use in our reports.
By default the latest baseline is used in reporting but since version 7.3 it’s possible to use up to ten baseline versions in your reporting
Any calendars in use are locked for editing if they are part of a baseline

## Slide 3: Baseline in Safran Project - Project properties
In the project properties or when you create a project – in the project setup, there are some settings that affect the baseline. You should know what these settings are and how they affect the baseline.
On the Scope tab is where we define what we want to include in the three different scopes available in Safran Project, the baseline scope, the current scope and the total scope.
First of all we can decide what type of resources we want to include in the scope – Planned or Contract. Keep it simple and stick to Planned.
Second, we must decide on what type of change orders should apply to each scope. More on change orders later.
Third, we can decide which scopes should be updated when we run a status update, and which should be updated when we run a baseline update.
Finally, we must decide on what scope we want to use to show progress at summary or group levels in the barchart editor.
Lock scope – this flag locks the scope for editing so that any changes to scope must be made using variation orders

## Slide 4: Baseline in Safran Project - Project properties
A lot of the options on the schedule settings tab apply to the analysis of the schedule, but it is also on this tab we can move our timenow date.
Timenow is the earliest date work can start in Safran Project.
When we set the original baseline we set timenow to the first day of the first reporting period of the project.
For example: If cut-offs are on Sundays, timenow must be set to Monday on the first reporting period of your project.
When we re-baseline our project, we move timenow to the first day of the next reporting period.
Moving timenow will push any remaining work forward to the new timenow date and any linked activities will be affected by this.
If you don’t move timenow when you set a new baseline you will overwrite your current baseline version (and if your current version is your first baseline you will also overwrite your original fields).

## Slide 5: The Baseline Process – Change Register
Change orders are separated into four types and are applied to scopes per your settings in the project properties. There is no definitive right way to use them, but here is a good guideline for what to put into your change order types:
  VO
  VO-request
  Internal Change
  Sub-Contracted
  Approved changes
  A request for change, will become a VO or declined
  Use this to make corrections to estimates that are off. Should be part of Baseline scope.
  Separate out external work you have in your plan

## Slide 6: Baseline in Safran Project
The processes related to baseline are found on the PROJECT ribbon, under the Baseline section:
Set Baseline
  The Original Baseline
  Re-baselining
Partial Baseline
Annul
Baseline Log

## Slide 7: Baseline in Safran Project
Set Baseline
  The Original Baseline
The process of running the first baseline is pretty straightforward. After you have made your preparations, you click the Set Baseline button, set a revision and add a comment and click OK.

## Slide 8: Baseline in Safran Project
Set Baseline
  Re-baselining
When re-baselining a project, we use the same Set Baseline button, but this time we have a couple more options. The new plan will not automatically recalculate all values from the new baseline.
A full calculation against the new baseline takes place at the next cutoff. So if new values for this baselines are required already now, this can be obtained by using these optional check boxes you see here:
  Overwrite historic frontline/planned %
  Sets frontline and planned % for Barchart Editor reports
  Update last status update with new baseline scope
  Sets history values for Histogram/S-curves and PSR
  Note: Increases in the baseline earned values will now occur immediately in the baseline period
There are a lot more preparations to keep in mind. You can review these in the baseline checklist document.

## Slide 9: Baseline in Safran Project
Partial Baseline
If you have a large increase in scope, you can add that scope to your current baseline using the Partial Baseline function. It could be that a whole new sub-project was added to your project, or unexpected obstacles were discovered in the early project phases that need to be added to your scope.
When you run a partial baseline you have the option of adding new activities and scope, or update scope or dates on existing activities.
The Baseline Resource Profiles checkbox allows you to update resource profiles on your baseline activities.

## Slide 10: Baseline in Safran Project
Partial Baseline
After you’ve decided what you want to update or add, you must set a filter. You must make a selection here, otherwise Safran Project will abort the baseline.

## Slide 11: Baseline in Safran Project
Partial Baseline
After you have set your filter you are shown a list of all the activities included in your partial baseline.
You can now review the changes and the previous values before you set the partial baseline.

## Slide 12: Baseline in Safran Project
Annul
Annulment lets you roll back a baseline. This can be useful if you found errors after setting a baseline and you need to go back to fix them.
Safran will always annul the latest or the current baseline – so no flexibility here – you annul sequentially backwards in the baselines available from your baseline log.

## Slide 13: Baseline in Safran Project
Baseline Log
Finally there’s the baseline log. A quick list to view all your baselines, when they were set, for what cutoff date, who set them, revision number and remarks.

## Slide 14: Errors and problems
These are some of the errors that can stop you from running a baseline:
You do not have update-access to all subprojects! You are not authorised to perform a baseline update on the project.
  Check your access to all subprojects and try to re-run the baseline
The project has not been assigned to a project-config
  Your project is missing a setup. Contact support.
No TimeNow has been assigned to the project
  Check TimeNow settings in Project Properties and re-run the baseline.
The Network TimeNow date must be a Monday
  Check TimeNow settings in Project Properties and re-run the baseline.
  Note! This may be any other weekday depending on the cutoff settings but is normally a Monday because cutoffs are normally sundays.
No cutoff found matching timenow
  Run a cutoff and re-run the baseline
The project is in a “Not Analysed” status. Please save project before running Baseline. Save project now? Yes/No
  Save project and re-run baseline
The project is still in a “Not Analysed” status. Probably because another user has made recent changes in the project. Please try to refresh data and then save! Yes/No
  Refresh with F5, save project and re-run baseline
You cannot run baseline with TimeNow set to <Date> when you already have run a baseline on <Date>
  This message comes when TimeNow is set to an earlier date than a previous baseline. Check TimeNow settings in Project Properties and re-run the baseline.

## Slide 15: Errors and problems - continued
These messages will come when you have progress inconsistencies between activities and resources. This may be related to how you pick up progress when you move TimeNow or other schedule conflicts that need to be addressed before running the baseline. Please refer to the baseline checklist or contact support.
Resource not complete – activity completed!
Resource not part of status update – activity completed!
Resource duration 0!
Resource pr. Day – not supported in baseline / status-update!