## Slide 1: Workshop: What is Best Practice Baseline Management?
Forum Safran 2019 | Facilitator Jørgen Aasland

## Slide 2: Agenda
Goal
What is Best Practice Baseline Management?
What is a Baseline?
Discussions
Summary

## Slide 3: Goals or why are we here today?
It Is my intention and goal to engage you in a few questions and the discussion related to baseline and the quest for a best practice.
What is your goal?
What do you expect to get out of this workshop?

## Slide 4: What is Best Practice Baseline Management?
A principle of performance measurement is that a baseline should be set at the planning stage and should not be altered unless due authority is received from the funding source.
Fix a baseline and measure performance against it. Only change the baseline when authorized to do so for clearly defined reasons. When a baseline is changed do not loose its original, set it and its successors in concrete.

## Slide 5: What is a Baseline?
What?
  What is a baseline?
  What should the baseline reflect?
  What are the benefits of having a baseline?
Why?
  Why do we set a baseline?
  Why do we keep updating the baseline?
When?
  When do we baseline?
  When do we re-baseline?
How?
  How do we set a baseline?
  How do we update the baseline?

## Slide 6: What is a Baseline?
What is a Baseline?
  A reference point
  Agreed upon scopes and milestones, hours and dates
  A contract and target
  A map
  A point to measure performance against
Why do we set and update a Baseline?
  To keep a history to measure against
  To measure performance
  To keep track of changes to scope
  It’s required in the contract
  To adjust the measurement point when new scope is added or budgets are revised every 6 or 12 months
When do we baseline and re-baseline?
  At the start of the project
  At contract defined periods, often every 6 or 12 months
  If there are major changes to scope or schedule that render the last baseline unusable as a reference point
How do we set and update the baseline?
  Get all stakeholders to agree on the proposed baseline plan
  Manage scope changes

## Slide 7: Agenda
Goal
What is Best Practice Baseline Management?
What is a Baseline?
Discussions
Summary

## Slide 8: What should be the focus of the initial Baseline?
The contract deliverables
Define the scope and schedule
An agreed upon scope and plan to measure against
Get ownership from the different disciplines responsible for executing the work
Milestones
What, how and when to deliver
Sufficient information to estimate cost, time and hours – be realistic (pessimistic)

## Slide 9: What are your main challenges when re-baselining?
Assure that you have enough time and the right people to contribute to the re-baseline process
Getting management to commit to the new baseline
Getting all input in time – have a plan!
Quality check all input
Budget strategy
Change management – unsetteled VO’s
Include performance data from previous baselines
Be realistic (pessimistic) when estimating

## Slide 10: What are the major differences between a baseline on a traditional project and a baseline on a program or a frame agreement?
Can be a mix of baselined and unbaselined projects in a portfolio
Using partial baseline to add new scope to a frame agreement
Using revised plan as a separate measurement point
Different focus on resources and having the right disciplines to perform work as new contracts and scope is added

## Slide 11: What can we (Safran) do to improve the processes required to set a Baseline?
Improve the manual
Provide a baseline checklist
Better explanation of the error messages related to baseline and what to do to make corrections
Better management of partial baselines, maybe provide extended scope history of the added partial baselines
Better explanation of what happens to resources with delay or progress
Workflow/processes for baseline in Safran
Track record for changes to partial baseline or any modifications on the original baseline
Provide an overall baseline on a project group

## Slide 12: Summary
Goal
What is Best Practice Baseline Management?
What is a Baseline?
Discussions
Summary

## Slide 13: Thank you